## Sheet1
Task | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6
Planning & Wireframing (Expected) | [6 empty] | Legend
Planning & Wireframing (Actual) | [7 empty] | Expected
Backend Setup (Expected) | [7 empty] | Actual
Backend Setup (Actual) | [7 empty] | Overdue
Frontend Development (Expected)
Frontend Development (Actual)
API Creation and Integration (Expected)
API Creation and Integration (Actual)
Testing (Expected)
Testing (Actual)
Deployment (Expected)
Deployment (Actual)

## Sheet2
Milestone | Task | Expected/Actual | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
 | time axis 2025-06-01 to 2025-07-22
Planning | Project Setup & Environment | Expected | bar: 2025-06-01 to 2025-06-04
Actual | bar: 2025-06-01 to 2025-06-04
| Technical Architecture Design | Expected | [52 empty] | Legend | bar: 2025-06-01 to 2025-06-04
Actual | bar: 2025-06-01 to 2025-06-04
| Database Schema Design | Expected | [53 empty] | Expected | bar: 2025-06-01 to 2025-06-04
|  | Actual | [53 empty] | Actual | bar: 2025-06-01 to 2025-06-04
| API Endpoints Planning | Expected | bar: 2025-06-01 to 2025-06-04
Actual | bar: 2025-06-01 to 2025-06-04
Wireframing | User Flow Diagram | Expected | bar: 2025-06-05 to 2025-06-07
Actual | bar: 2025-06-05 to 2025-06-07
| Low-fidelity Wireframes | Expected | bar: 2025-06-05 to 2025-06-07
Actual | bar: 2025-06-05 to 2025-06-07
Database & Infrastructure | PostgreSQL Database Setup | Expected | bar: 2025-06-08 to 2025-06-12
Actual | bar: 2025-06-08 to 2025-06-12
| Prisma ORM Configuration | Expected | bar: 2025-06-08 to 2025-06-12
Actual | bar: 2025-06-08 to 2025-06-12
| AWS S3 Bucket Configuration | Expected | bar: 2025-06-08 to 2025-06-12
Actual | bar: 2025-06-08 to 2025-06-12
| Environment Configuration | Expected | bar: 2025-06-08 to 2025-06-12
Actual | bar: 2025-06-08 to 2025-06-12
Authentication System | Firebase Admin SDK Setup | Expected | bar: 2025-06-13 to 2025-06-14
Actual | bar: 2025-06-13 to 2025-06-14
| Authentication Middleware | Expected | bar: 2025-06-13 to 2025-06-14
Actual | bar: 2025-06-13 to 2025-06-14
Basic API Structure | Express Server Setup | Expected | bar: 2025-06-15 to 2025-06-17
Actual | bar: 2025-06-15 to 2025-06-17
| User Management API | Expected | bar: 2025-06-15 to 2025-06-17
Actual | bar: 2025-06-15 to 2025-06-17
Backend API Development | Project CRUD Operations APIs | Expected | bar: 2025-06-18 to 2025-06-21
Actual | bar: 2025-06-19 to 2025-06-22
| User Management APIs | Expected | bar: 2025-06-18 to 2025-06-21
Actual | bar: 2025-06-18 to 2025-06-20
| Member Invitation APIs | Expected | bar: 2025-06-18 to 2025-06-21
Actual | bar: 2025-06-19 to 2025-06-20
| Meeting Scheduling APIs | Expected | bar: 2025-06-18 to 2025-06-21
Actual
| Project Details Export APIs | Expected | bar: 2025-06-18 to 2025-06-21
Actual | bar: 2025-06-20 to 2025-06-21
| Task Completion Review API | Expected | bar: 2025-06-18 to 2025-06-21
Actual | bar: 2025-06-21 to 2025-06-22
Core React Setup | React App Initialization | Expected | bar: 2025-06-01 to 2025-06-03; 2025-06-22 to 2025-06-23
Actual | bar: 2025-06-01 to 2025-06-02; 2025-06-22
| Routing & Navigation Setup | Expected | bar: 2025-06-22 to 2025-06-24
Actual | bar: 2025-06-23 to 2025-06-24
Authentication Components | Firebase Client Setup | Expected | bar: 2025-06-01 to 2025-06-03; 2025-06-23 to 2025-06-24
Actual | bar: 2025-06-01 to 2025-06-02; 2025-06-22 to 2025-06-23
| Login/Register Components | Expected | bar: 2025-06-25 to 2025-06-27
Actual | bar: 2025-06-24 to 2025-06-25
Core UI Components | Dashboard Layout | Expected | bar: 2025-06-28 to 2025-07-04
Actual | bar: 2025-06-28 to 2025-06-29; 2025-07-02 to 2025-07-04
| Project Management Interface | Expected | bar: 2025-06-28 to 2025-07-04
Actual | bar: 2025-06-30 to 2025-07-02
| Member Invitation Interface | Expected | bar: 2025-06-28 to 2025-07-04
Actual | bar: 2025-06-30 to 2025-07-02; 2025-07-07
| Timeline Interface | Expected | bar: 2025-06-28 to 2025-07-04
Actual | bar: 2025-07-03 to 2025-07-05
| Task Completion - Proof Submission Interface | Expected | bar: 2025-06-28 to 2025-07-04
Actual | bar: 2025-07-04 to 2025-07-06; 2025-07-08
| Task Completion - Verification Interface | Expected | bar: 2025-06-28 to 2025-07-04
Actual | bar: 2025-07-06 to 2025-07-08
Frontend-Backend Integration | Authentication Integration | Expected | bar: 2025-07-05 to 2025-07-06
Actual | bar: 2025-07-02 to 2025-07-03
| Project Management Integration | Expected | bar: 2025-07-05 to 2025-07-06
Actual | bar: 2025-07-06 to 2025-07-07
| Task Management Integration | Expected | bar: 2025-07-05 to 2025-07-06
Actual | bar: 2025-07-08 to 2025-07-09
| User Management Integration | Expected | bar: 2025-07-05 to 2025-07-06
Actual | bar: 2025-07-08 to 2025-07-09
| Member Invitation Integration | Expected | bar: 2025-07-05 to 2025-07-06
Actual | bar: 2025-07-09
| Project Details Export Integration | Expected | bar: 2025-07-05 to 2025-07-06
Actual | bar: 2025-07-02 to 2025-07-03; 2025-07-11 to 2025-07-12
| Task Completion Review Integration | Expected | bar: 2025-07-05 to 2025-07-06
Actual | bar: 2025-07-13
Testing | Unit Testing - API Endpoints | Expected | bar: 2025-07-07 to 2025-07-09
Actual | bar: 2025-07-13 to 2025-07-15
| Authentication Testing | Expected | bar: 2025-07-07 to 2025-07-09
Actual | bar: 2025-07-16
| Unit Testing - UI Components | Expected | bar: 2025-07-07 to 2025-07-09
Actual | bar: 2025-07-16 to 2025-07-17
| Integration Testing - UI & Database | Expected | bar: 2025-07-07 to 2025-07-09
Actual | bar: 2025-07-16
| End-to-End Testing | Expected | bar: 2025-07-07 to 2025-07-09
Actual | bar: 2025-07-16 to 2025-07-17; 2025-07-21 to 2025-07-22
| Cross-browser Testing | Expected | bar: 2025-07-07 to 2025-07-09
Actual | bar: 2025-07-19; 2025-07-22
Deployment Setup | Production Environment Setup | Expected | bar: 2025-07-10 to 2025-07-12
Actual | bar: 2025-07-12 to 2025-07-14
| CI/CD Pipeline Configuration | Expected | bar: 2025-07-10 to 2025-07-12
Actual | bar: 2025-07-13 to 2025-07-15