## Sheet1
Task | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6
Planning & Wireframing (Expected) | [6 empty] | Legend
Planning & Wireframing (Actual) | [7 empty] | Expected
Backend Setup (Expected) | [7 empty] | Actual
Backend Setup (Actual) | [7 empty] | Overdue
Frontend Development (Expected)
Frontend Development (Actual)
API Creation and Integration (Expected)
API Creation and Integration (Actual)
Testing (Expected)
Testing (Actual)
Deployment (Expected)
Deployment (Actual)

## Sheet2
Milestone | Task | Expected/Actual | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41
Planning | Project Setup & Environment | Expected | bar: Week 1 1 to Week 1 4
Actual | bar: Week 1 1 to Week 1 4
| Technical Architecture Design | Expected | [41 empty] | Legend | bar: Week 1 1 to Week 1 4
Actual | bar: Week 1 1 to Week 1 4
| Database Schema Design | Expected | [42 empty] | Expected | bar: Week 1 1 to Week 1 4
|  | Actual | [42 empty] | Actual | bar: Week 1 1 to Week 1 4
| API Endpoints Planning | Expected | bar: Week 1 1 to Week 1 4
Actual | bar: Week 1 1 to Week 1 4
Wireframing | User Flow Diagram | Expected | bar: Week 1 5 to Week 1 7
Actual | bar: Week 1 5 to Week 1 7
| Low-fidelity Wireframes | Expected | bar: Week 1 5 to Week 1 7
Actual | bar: Week 1 5 to Week 1 7
Database & Infrastructure | PostgreSQL Database Setup | Expected | bar: Week 2 8 to Week 2 12
Actual | bar: Week 2 8 to Week 2 12
| Prisma ORM Configuration | Expected | bar: Week 2 8 to Week 2 12
Actual | bar: Week 2 8 to Week 2 12
| AWS S3 Bucket Configuration | Expected | bar: Week 2 8 to Week 2 12
Actual | bar: Week 2 8 to Week 2 12
| Environment Configuration | Expected | bar: Week 2 8 to Week 2 12
Actual | bar: Week 2 8 to Week 2 12
Authentication System | Firebase Admin SDK Setup | Expected | bar: Week 2 13 to Week 2 14
Actual | bar: Week 2 13 to Week 2 14
| Authentication Middleware | Expected | bar: Week 2 13 to Week 2 14
Actual | bar: Week 2 13 to Week 2 14
Basic API Structure | Express Server Setup | Expected | [41 empty] | Enhancements | bar: Week 3 15 to Week 3 17
Actual | bar: Week 3 15 to Week 3 17
| User Management API | Expected | bar: Week 3 15 to Week 3 17
Actual | bar: Week 3 15 to Week 3 17
Backend API Development | Project CRUD Operations APIs | Expected | bar: Week 3 18 to Week 3 21
Actual | bar: Week 3 18 to Week 3 21
| User Management APIs | Expected | bar: Week 3 18 to Week 3 21
Actual | bar: Week 3 18 to Week 3 21
| Member Invitation APIs | Expected | bar: Week 3 18 to Week 3 21
Actual | bar: Week 3 18 to Week 3 21
| Meeting Scheduling APIs | Expected | bar: Week 3 18 to Week 3 21
Actual | bar: Week 3 18 to Week 3 21
| Project Details Export APIs | Expected | bar: Week 3 18 to Week 3 21
Actual | bar: Week 3 18 to Week 3 21
| Task Completion Review API | Expected | bar: Week 3 18 to Week 3 21
Actual | bar: Week 3 18 to Week 3 21
Core React Setup | React App Initialization | Expected | bar: Week 4 22 to Week 4 24
Actual | bar: Week 4 22 to Week 4 24
| Routing & Navigation Setup | Expected | bar: Week 4 22 to Week 4 24
Actual | bar: Week 4 22 to Week 4 24
Authentication Components | Firebase Client Setup | Expected | bar: Week 4 25 to Week 4 27
Actual | bar: Week 4 25 to Week 4 27
| Login/Register Components | Expected | bar: Week 4 25 to Week 4 27
Actual | bar: Week 4 25 to Week 4 27
Core UI Components | Dashboard Layout | Expected | bar: Week 4 28 to Week 5 34
Actual | bar: Week 4 28 to Week 5 34
| Project Management Interface | Expected | bar: Week 4 28 to Week 5 34
Actual | bar: Week 4 28 to Week 5 34
| Member Invitation Interface | Expected | bar: Week 4 28 to Week 5 34
Actual | bar: Week 4 28 to Week 5 34
| Timeline Interface | Expected | bar: Week 4 28 to Week 5 34
Actual | bar: Week 4 28 to Week 5 34
| Task Completion - Proof Submission Interface | Expected | bar: Week 4 28 to Week 5 34
Actual | bar: Week 4 28 to Week 5 34
| Task Completion - Verification Interface | Expected | bar: Week 4 28 to Week 5 34
Actual | bar: Week 4 28 to Week 5 34
Frontend-Backend Integration | Authentication Integration | Expected | bar: Week 5 35 to Week 6 36
Actual | bar: Week 5 35 to Week 6 36
| Project Management Integration | Expected | bar: Week 5 35 to Week 6 36
Actual | bar: Week 5 35 to Week 6 36
| Task Management Integration | Expected | bar: Week 5 35 to Week 6 36
Actual | bar: Week 5 35 to Week 6 36
| User Management Integration | Expected | bar: Week 5 35 to Week 6 36
Actual | bar: Week 5 35 to Week 6 36
| Member Invitation Integration | Expected | bar: Week 5 35 to Week 6 36
Actual | bar: Week 5 35 to Week 6 36
| Meeting Scheduling Integration | Expected | bar: Week 5 35 to Week 6 36
Actual | bar: Week 5 35 to Week 6 36
| Project Details Export Integration | Expected | bar: Week 5 35 to Week 6 36
Actual | bar: Week 5 35 to Week 6 36
| Task Completion Review Integration | Expected | bar: Week 5 35 to Week 6 36
Actual | bar: Week 5 35 to Week 6 36
Testing | Unit Testing - API Endpoints | Expected | bar: Week 6 37 to Week 6 39
Actual | bar: Week 6 37 to Week 6 39
| Authentication Testing | Expected | bar: Week 6 37 to Week 6 39
Actual | bar: Week 6 37 to Week 6 39
| Unit Testing - UI Components | Expected | bar: Week 6 37 to Week 6 39
Actual | bar: Week 6 37 to Week 6 39
| Integration Testing - UI & Database | Expected | bar: Week 6 37 to Week 6 39
Actual | bar: Week 6 37 to Week 6 39
| End-to-End Testing | Expected | bar: Week 6 37 to Week 6 39
Actual | bar: Week 6 37 to Week 6 39
| Cross-browser Testing | Expected | bar: Week 6 37 to Week 6 39
Actual | bar: Week 6 37 to Week 6 39
Deployment Setup | Production Environment Setup | Expected | bar: Week 6 40 to Week 6 41
Actual | bar: Week 6 40 to Week 6 41
| CI/CD Pipeline Configuration | Expected | bar: Week 6 40 to Week 6 41
Actual | bar: Week 6 40 to Week 6 41